## Release Backlog
Finance Credit - Release Backlog
RELEASE BACKLOG
SPRINT | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES |  | STATUS KEY | WORK ESTIMATE IN HOURS
|  |  |  | 1 | Completed |  |  | Not Started | 1
Week 5 | Lucid Chart |  | Team | 1 | Completed | This went well, we communicated effectively, and responsibilities were shared. |  | In Progress | 2
Week 10 | Interview Questions | Over the course of the semester, each person will have to interview 3 people, so it's better to start thinking about it earlier. A great place to look for categories of people to interview will be the class document that we'll have out by wednesday. Here's a draft Mabel made for the medical devices team if you want to use it for reference. | Team | 1 | In Progress | This went well, we have a generic outline of the interview questions we would like to ask. Still have not completed the interviews themselves. | This went well, we have a generic outline of the interview questions we would like to ask. Still have not completed the fir | Completed | 4
Week 6 | Detailed Product Vision Document | Identify classes (see chapter 4 slides 12-19 here for reference: https://mtu.instructure.com/courses/1467600/pages/slide-materials?wrap=1) that will be relevant to your team. We will have a google sheet similar to the vision document to fill this out on wednesday. Similar to features, many of the classes will have overlap between teams, so this is a good way to avoid duplicating work. |  | 1 | Not Started |  |  |  | 8
Week 3 | High Overview Product Class Brainstorm |  | Team | 1 | Completed | This went well. Lots of ideas were thrown on the table. In the future, we could utilize diffrent brainstorming techniques. |  |  | 16
Week 5 | Identify features | Identify which of the features in the list from the vision document is most central to your team. Make a process map for this feature | Team | 1 | Completed | Team agrees that this was completed to a satisfactory level. Could potentially improve upon the efficency in coming up with features in the future. |  |  | 24
Week 6 | Sketch out basic protype | While this could have code, at the moment we're mostly looking for a general idea of what your teams product will look like. Again, we're looking to have an example out by wednesday night; but if you want to start early there are a number of ways to go about it. | Team | 1 | In Progress |  |  |  | 40
Week 6 | Create release Backlog |  |  | 1 | In Progress |  |  |  | 80
1
1
1
1
1

## Tasks
Finanace Credit - Tasks
TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED
Prototype | Identify product features that you can analyze, design, and prototype.
Understand the problem domain | Understand the problem domain and the users in the problem domain to design a customer- centered product. Be Agile. Don’t conduct all interviews in one deliverable. Spread out the potential customer contact across all of the deliverables to maximize learning and feedback.
Benchmarking | Benchmark in detail existing solutions (IT and non-IT solutions) (both competing and complementary products) and the companies that provide them.
Interview | Interview (NOT SURVEY) many diverse users/stakeholders (remotely (i.e., Zoom) or in person) to understand the problem domain (e.g., interviews, focus groups, etc.) and needs for a solution.
Analyze Interview | Analyze the interviews and document important aspects of the problem domain. Examples of details include: o The environment in which people encounter the problem (e.g., at home, traveling, in the office, in quiet settings, in loud settings, etc.). o The specific frustrations/pain points they experience. o The causes of the frustrations/pain points. o What motivates individuals to engage within the problem domain in the first place? o The processes people go through within the problem domain. o Use diagrams to present your findings in an easily digestible format. o Empathize with the user to better understand their needs.
Design an information system | Design an information system with analytics/machine learning capabilities that will solve the identified problem/opportunity. o Design as you interview and analyze the problem. Don’t wait to start designing. In this way, you will use an Agile management approach. o Document the expected process users will go through when using the product (i.e., activity diagrams, business process & mapping notation, story boards).  Identify exception conditions that could cause the expected process to break down. Document how your system will help to redirect users back to the expected process. o A domain class diagram or entity relationship diagram demonstrating the various “things” in the problem domain that the system must keep track of. o A visual representation of the user interface, such as with Adobe XD, Figma, or even with hand drawn mockups. o Other diagrams that might be useful to explain the design of your system to teammates or other stakeholders. Relevant documents that do not provide details about individuals (such as interview
Prototype the information system. | • Prototype the information system. o Prototype as you analyze and design. Don’t wait to create early simple prototypes (even early paper-based mockups). Use an Agile management approach. Get started as soon as you can. Don’t be afraid to start coding by even Deliverable 1. o The final prototype must include working code. o You do not necessarily have to write the code yourselves, but many in the class will be able to contribute to coding. A programming textbook will also be provided for your reading. Be creative and consider how you could outsource parts of the coding to a Michigan Tech Enterprise, or outsource work to another course with a programming project, etc. Don’t be shy and don’t wait to do this. Many classes choose projects early in the semester. Managers have to be able to find and obtain resources. Act accordingly.
Test the prototype with 80+ potential users. | Test the prototype with 80+ potential users. o Design a test or a series of tests to assess the quality, desirability, and user satisfaction of the product features and overall prototype. o Each person in the course should test a feature or the overall prototype with at least 2 people to give everyone the experience of getting user/customer feedback. o Document the users’ feedback and suggestions. o Testing should happen throughout the semester as you continue to develop your prototype. Use an Agile management approach. o Based on collective feedback from prototype testing, refine and improve the feature or overall prototype. This should be an ongoing process. Don’t perform all tests at the same 6 This project is subject to change as needed time. Spread them throughout the semester so that your prototype improves week by week.
Develop a business case report to identify how you would commercialize the product and create a profitable company. | Outline in detail the costs of maintaining the system (e.g., labor costs, management costs, infrastructure costs, etc.). o The plan should estimate reasonable sales forecasts and identify pricing strategies for the product to be viable. o If the product isn’t enough to start an entire business around, document the other products and services you would need to provide as a company. These additional products should be included in the costs and pricing strategies. o At a high level, show me that you have a viable idea that investors would be interested in.
Final Report and Presentation | Create a 15-30 page business case report to outline the product and your business model with at least the following (note this is a simplified version of a business plan): a. Well-written executive summary (1-3 pages; ~10% of paper length) i. An overview of the business idea ii. A brief description of the product iii. An introduction to the goals for the business iv. An introduction to the target market v. An introduction to existing competitors and why your solution will or won’t gain traction in the market vi. An overview of the financial estimates and profit potentials
b. Company Description | i. Mission statement ii. Core values iii. Key goals iv. Introduction of the industry/market and the outlook for the entire industry. How and why will the product/business fit within the industry
c. Product | i. Describe the product you developed and any other complementary products/services you would offer if you started a company around the product ii. Identify the problem the service solves or opportunity that it exploits iii. Describe the product features that solve the problem and that provide a competitive advantage 1. Include product documentation/screenshots/etc.
Marketing | i. Size of the total market and market trends (i.e., expected growth trends of the entire market) ii. Target market – describe the target market (such as detailed user profiles) in detailiii. What percent of the total market is your target market and what are trends within that target market? iv. Who are the major competitors in the market, how much market share do they hold, and how much market share do you reasonably think you can get? v. What barriers to entry exist within the market/industry? How would you overcome them? vi. How will you market the product to the target market? vii. How much will marketing efforts cost? viii. Detailed explanation of the pricing model with justification ix. A reasonable one-year sales forecast. Don’t assume you will have 100% market share. That isn’t reasonable. Use sensitivity analysis to adjust assumptions to show a range of possible outcomes.
e. Operations | i. How would you continue to develop and refine the product and other related products? ii. How will you ensure the quality of the product? iii. What personnel would be required to further develop and maintain the product(s). Many companies hire individuals who simply work on open source projects. iv. How/where will you “host” the product (e.g., Google Cloud, AWS, dedicated server from host, on site server)
f. Management | i. What would the management structure of the company look like? ii. How would you find appropriate managers to fill in knowledge gaps? iii. What advisors would you need (e.g., attorney, CPA, etc.) iv. What would the organizational chart look like?
g. Startup Expenses and Financial Plan | i. How much capital would you need to start a business and sell a finished product? ii. How would the needed capital be used (e.g., salaries, office space (if needed), contingency spending, etc.)? Break it down in detail, both textually and in tables. Tables don’t always speak for themselves unless well designed. iii. How long will finishing the development of the product take? iv. Projections for profits and losses for the first 3 years of operation based on your previously outlined costs, market share, and pricing strategy. These projections should be very detailed based on costs, your pricing strategy, etc. Spreadsheets can be included as additional detail. v. When will initial investments in product development
h. Appendices (for the instructor’s grading purposes) | i. All documentation/models you created when designing the solution ii. Interview notes and other documentation iii. Prototype screenshots iv. Updated charter v. Updated vision document